## Sheet1
Risk | Risk Receptor | Median Risk Score | Maximum Risk Score | Potential Impact Description | Root Cause | SDLC Phase
A databreach within the ERP system could result in customer record loss or compromise | Financial (fines, settlements) Reputation (customer confidence) | 1.65 | 1.826 | Unauthorized access or release of PII or intelectual property | lack of application security and data encryption at rest | System Design Testing
Business decision errors resulting from incomplete or inacurate data | Financial (forcasting, reporting) | 1.364 | 1.5397 | The ERP may continue to generate data output that appears correct until reviewed by another party. | Human error or Software error, (syntactical or bug) | N/A
ERP Developer does not offer Cyber Incident Response Team (CIRT) support | Full Spectrum of risk based on exponential impact to multiple systems | 1.2375 | 1.665 | In-house staff must be trained in specialty skills or external cyber consultant retained to be part of CIRT. |  | N/A
Customer service issues resulting from incomplete or inacurate data | Reputation (customers: missed deliveries, invoicing mistakes) Financial (performance penalties) | 1.1083 | 1.2125 | The ERP may continue to generate data output that appears correct until reviewed by another party. | Human error or Software error, (syntactical or bug) | N/A
ERP implementation unavailiable or unusable | Financial ( productivity), | 1.086 | 1.184 | The system performance results in workers taking longer to perform their tasks than with the existing spreadsheet systems | Technical system capacity or performance planning, | Installation & UAT
ACME staff slow or resistent to adopting ERP workflow | Business operations, financial, reputational | 1.0642 | 1.2735 | Users and business functions continue to rely on legacy spreadsheet mode of operation | Organizational culture, implementation approach, lack of leadership support, lack of useer training | Installation and UAT
ERP implementation delays lead to cost overruns | Financial | 1.0552 | 1.2913 | Existing business process(es) require ERP software configuration outside of standard implementation | Acme unaware of process complexity or all business areas involved in process Implementation team is not capable of identifying resolutions | Installation & UAT
ERP developers can not produce feature enhancements Acme requires | Business operations, financial, reputational | 1.05 | 1.05 | Changes to business operational requirements over time must be anticpated | Supply chain management error Management decision to use in house resources | Operations & Maintenance
CIRT does not maintain high level of readiness through regular CIRT exercises in response/recovery. | Full Spectrum of risk based on exponential impact to multiple systems | 0.96667 | 0.96667 | Response/recovery in real world incident is delayed and inefective |  | N/A
ACME IT department unable to adequately support ERP environment | Full Spectrum of risk based on exponential impact to multiple systems | 0.94833 | 1.21 | Unplanned service disruptions to certain ERP capabilites or the entire system extend for hours, days or occur frequently in business hours | ERP support may require specialized skills that are not adequately funded | Operations & Maintenance
Initial customization creates future maintenance difficulties and technical debt | Operational, Financial, Reputational (including this team who recommended the selection) | 0.93358 | 1.0937 | Limitations with the ERP selected can only be resolved through bespoke modifications | Senior management unprepared to support setbacks uncovered during implementation. | System Design Development
ERP implementation requirments create resource conflicts with existing operational staff | Financial, reputational (internal stakeholders) | 0.9 | 0.9 | Current business operations need to run in parallel while new ERP is implemented, tested and transferred into production | Senior management unprepared to fund additional resources, Project management failing to identify constraints early and escalate resolutions | N/A
Modifications to one ERP module unknowingly affect other modules resulting in incomplete or inacurate data | Full Spectrum of risk based on exponential impact to multiple systems | 0.88833 | 0.97375 | Delay in discovery of erroneous data use or malware spread results in multiple system involvement, delayed response/recovery and potential fines or civil litigation | The complexity of change not adequately addressed | Testing
Organizational change delays lead to cost overruns | Financial, reputational (internal stakeholders) | 0.76667 | 0.76667 | Business process changes to meet ERM requirements difficult to implement in various Acme business areas | Limited understanding of current operational requirements Employees not aligned with senior management | Installation & UAT
Limited benefits realization results in board of directors/investor confidence issue | Business operations, financial, reputational | 0.741 | 0.9685 | Implementation issues lead to only basic ERP capabilities in place or inability to retire some legacy processes | Senior management unprepared to support setbacks uncovered during implementation. | System Analysis & Requirements
ERP Developers fail to timely, discover, inform and patch for new vulnerabilities. | Full Spectrum of risk based on exponential impact to multiple systems | 0.696 | 0.788 | Security Patches are not implemented quickly enough to prevent a breach or exploited vulnerability |  | Operations & Maintenance
ERP software obselecance due to vendor failure or development team failure | Operational, Financial, Reputational | 0.66875 | 0.985 | All software will become obsolete, which lifecycle management approach best fits ACME. |  | Operations & Maintenance
Difficulty/inability to import or export data leads to solution lock-in or parallel sysems | Loss of revenue, loss of efficiency/employee satisfaction | 0.57867 | 0.74434 | Existing organizational data must put into the ERP, data will need to be extract in the future when moving to a new platform | Lack of enterprise architecture and data requirements | Development (technical debt) System Design
ERP developers can not produce vulnerabilty fixes at the rate Acme requires | Full Spectrum of risk based on exponential impact to multiple systems | 0.556 | 0.748 | Software updates will be needed to mitigate security vulnerabilties when they are discovered - Custom solutions result in delays (extended vulnerability timeframe) | Supply chain management error Management decision to use in house resources | Operations & Maintenance
ERP solution lacks reporting capability for transactions that potentially violate segregation of duties controls | Financial, reputational (internal stakeholders) | 0.30767 | 0.4225 | The ability to monitor transactions for potential issues and highlight those that must be manually reviewed is an important detective control |  | System Analysis & Requirements
Lack of legal recourse to recover costs due to ERP implementation or performance failure | Financial | 0.3 | 0.3 | Damage claims by ERP clients are not uncommon, | Supply chain management error Management decision to use in house resources | N/A
ERP solution lacks adequately robust role based access controls to enforce the segregation of duties required | Business operations, financial | 0.20025 | 0.3 | Segregation of duties is a key control for preventing fraud, misuse or misallocation of enterprise resources |  | System Analysis & Requirements