## ERM Assessment Summary
Risk ID | Risk | Risk Receptor | Median Risk Score | Maximum Risk Score | Primary or Seconday Loss | Potential Impact Description | Root Cause | Triggers | SDLC Phase
1 | Initial customization creates future maintenance difficulties and technical debt | Operational, Financial, Reputational (including this team who recommended the selection) | 0.93358 | 1.0937 | Secondary | Limitations with the ERP selected can only be resolved through bespoke modifications | Senior management unprepared to support setbacks uncovered during implementation. | Time and cost presures on project deliverlables can result in workaround solutions. | System Design Development
2 | ERP software obselecance due to vendor failure or development team failure | Operational, Financial, Reputational | 0.66875 | 0.985 | Secondary | All software will become obsolete, which lifecycle management approach best fits ACME. |  |  | Operations & Maintenance
3 | Difficulty/inability to import or export data leads to solution lock-in or parallel sysems | Loss of revenue, loss of efficiency/employee satisfaction | 0.57867 | 0.74433 | Primary | Existing organizational data must put into the ERP, data will need to be extract in the future when moving to a new platform | Lack of enterprise architecture and data requirements | Proprietary data storage, lack of prebuilt extract, transform and load capabilities , Limited use of common open standards such as rest APIs | Development (technical debt) System Design
4 | Lack of legal recourse to recover costs due to ERP implementation or performance failure | Financial | 0.3 | 0.3 | Secondary | Damage claims by ERP clients are not uncommon, | Supply chain management error Management decision to use in house resources | Contracts limit liablity of the software vendor and/or implementer The company develops it's own software and assumes all related risks | N/A
[10 empty] | Proposed Controls from NIST SP800-53 | Category/Type of Controls
5 | ERP implementation delays lead to cost overruns | Financial | 1.0552 | 1.2913 | Primary | Existing business process(es) require ERP software configuration outside of standard implementation | Acme unaware of process complexity or all business areas involved in process Implementation team is not capable of identifying resolutions | Unforseen difficulty modeling existing business process(es) in ERP software | Installation and UAT | SLA | Admin
6 | Organizational change delays lead to cost overruns | Financial, reputational (internal stakeholders) | 0.76667 | 0.76667 | Primary | Business process changes to meet ERM requirements difficult to implement in various Acme business areas | Limited understanding of current operational requirements Employees not aligned with senior management | ERP implementation delays due to business process change requirements | Installation and UAT | Internal SLA | Admin
7 | ERP implementation requirments create resource conflicts with existing operational staff | Financial, reputational (internal stakeholders) | 0.9 | 0.9 | Primary | Current business operations need to run in parallel while new ERP is implemented, tested and transferred into production | Senior management unprepared to fund additional resources, Project management failing to identify constraints early and escalate resolutions |  | N/A | Internal SLA | Admin
8 | A databreach within the ERP system could result in customer record loss or compromise | Financial (fines, settlements) Reputation (customer confidence) | 1.65 | 1.826 | Primary & Secondary | Unauthorized access or release of PII or intelectual property | lack of application security and data encryption at rest | System compromise such as data theft through application injection, ransomware or poor IT management practices | System Design Testing | Access Control Suite as applicable | Admin/Technical
9 | ERP developers can not produce vulnerabilty fixes at the rate Acme requires | Full Spectrum of risk based on exponential impact to multiple systems | 0.556 | 0.748 | Primary | Software updates will be needed to mitigate security vulnerabilties when they are discovered - Custom solutions result in delays (extended vulnerability timeframe) | Supply chain management error Management decision to use in house resources | Vendor or project community is slow to release security fixes or they are not stable Internal development team lacks expertise or time to develop security fixes | Operations & Maintenance | SLA, Automated Processes (RA-5 Automated Monitoring) (Implemented by Acme) | Admin/Technical
10 | ERP Developers fail to timely, discover, inform and patch for new vulnerabilities. | Full Spectrum of risk based on exponential impact to multiple systems | 0.696 | 0.788 | Primary | Security Patches are not implemented quickly enough to prevent a breach or exploited vulnerability |  |  | Operations & Maintenance | SLA, Automated Processes (RA-5 Automated Monitoring & Distribute) | Admin/Technical
11 | CIRT does not maintain high level of readiness through regular CIRT exercises in response/recovery. | Full Spectrum of risk based on exponential impact to multiple systems | 0.96667 | 0.96667 | Primary & Secondary | Response/recovery in real world incident is delayed and inefective |  |  | N/A | SLA (includes CIRT members from Developer), Policy (requires reglular CIRT exercises and AARs) | Admin
12 | ERP Developer does not offer Cyber Incident Response Team (CIRT) support | Full Spectrum of risk based on exponential impact to multiple systems | 1.2375 | 1.665 | Primary | In-house staff must be trained in specialty skills or external cyber consultant retained to be part of CIRT. |  |  | N/A | SLA with external CIRT consultant, Internal training and exercises | Admin
13 | ERP implementation unavailiable or unusable | Financial ( productivity), | 1.086 | 1.184 | Primary | The system performance results in workers taking longer to perform their tasks than with the existing spreadsheet systems | Technical system capacity or performance planning, | System performance is unacceptable due to sizing or equipment failure | Installation and UAT | Business users participation in design decisions | Admin
14 | Business decision errors resulting from incomplete or inacurate data | Financial (forcasting, reporting) | 1.364 | 1.5397 | Primary | The ERP may continue to generate data output that appears correct until reviewed by another party. | Human error or Software error, (syntactical or bug) | Users struggle with data input into the new system | N/A | Business users participation in UAT | Admin
15 | Customer service issues resulting from incomplete or inacurate data | Reputation (customers: missed deliveries, invoicing mistakes) Financial (performance penalties) | 1.1083 | 1.2125 | Secondary | The ERP may continue to generate data output that appears correct until reviewed by another party. | Human error or Software error, (syntactical or bug) | Users struggle with data input into the new system | N/A | Business users participation in UAT | Admin
16 | Modifications to one ERP module unknowingly affect other modules resulting in incomplete or inacurate data | Full Spectrum of risk based on exponential impact to multiple systems | 0.88833 | 0.97375 | Primary | Delay in discovery of erroneous data use or malware spread results in multiple system involvement, delayed response/recovery and potential fines or civil litigation | The complexity of change not adequately addressed | Time constraints on change implementation and testing, lack of funding for a comprehensive test and development area | Testing | IT department participation in design decisions, SLA requiring sysstem monitoring | Admin/Technical
17 | ACME IT department unable to adequately support ERP environment | Full Spectrum of risk based on exponential impact to multiple systems | 0.94833 | 1.21 | Primary | Unplanned service disruptions to certain ERP capabilites or the entire system extend for hours, days or occur frequently in business hours | ERP support may require specialized skills that are not adequately funded | A complex architecture that is difficult to maintain SME orgnaizations often have limited I.T. specialist resources | Operations & Maintenance | Internal SLA | Admin
18 | Limited benefits realization results in board of directors/investor confidence issue | Business operations, financial, reputational | 0.741 | 0.9685 | Secondary | Implementation issues lead to only basic ERP capabilities in place or inability to retire some legacy processes | Senior management unprepared to support setbacks uncovered during implementation. | Communication issues between departments, project management fails to identify and escalate risks and roadblocks | System Analysis & Requirements |  | Admin
19 | ACME staff slow or resistent to adopting ERP workflow | Business operations, financial, reputational | 1.0642 | 1.2735 | Primary | Users and business functions continue to rely on legacy spreadsheet mode of operation | Organizational culture, implementation approach, lack of leadership support, lack of useer training | Workers citiing system inacuracy, system use difficulty or tacit management acceptance of poor adoption | Installation and UAT | Management enforced decison | Admin
20 | ERP developers can not produce feature enhancements Acme requires | Business operations, financial, reputational | 1.05 | 1.05 | Primary | Changes to business operational requirements over time must be anticpated | Supply chain management error Management decision to use in house resources | Vendor or project community is slow to release new features or they are not stable Internal development team lacks expertise or time to develop new features | Operations & Maintenance | SLA, Internal SLA | Admin
21 | ERP solution lacks adequately robust role based access controls to enforce the segregation of duties required | Business operations, financial | 0.20025 | 0.3 | Primary & Secondary | Segregation of duties is a key control for preventing fraud, misuse or misallocation of enterprise resources |  |  | System Analysis & Requirements | SLA requiring audits and automated monitoring | Admin/Technical
22 | ERP solution lacks reporting capability for transactions that potentially violate segregation of duties controls | Financial, reputational (internal stakeholders) | 0.30767 | 0.4225 | Secondary | The ability to monitor transactions for potential issues and highlight those that must be manually reviewed is an important detective control |  |  | System Analysis & Requirements | SLA requiring audits | Admin
Note on B31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is this an appliclabe threat for an internal ERP?

## ERM Summary Chart Content
Risk | Risk Receptor | Median Risk Score | Maximum Risk Score | Potential Impact Description | Root Cause | SDLC Phase
A databreach within the ERP system could result in customer record loss or compromise | Financial (fines, settlements) Reputation (customer confidence) | 1.65 | 1.826 | Unauthorized access or release of PII or intelectual property | lack of application security and data encryption at rest | System Design Testing
Business decision errors resulting from incomplete or inacurate data | Financial (forcasting, reporting) | 1.364 | 1.5397 | The ERP may continue to generate data output that appears correct until reviewed by another party. | Human error or Software error, (syntactical or bug) | N/A
ERP Developer does not offer Cyber Incident Response Team (CIRT) support | Full Spectrum of risk based on exponential impact to multiple systems | 1.2375 | 1.665 | In-house staff must be trained in specialty skills or external cyber consultant retained to be part of CIRT. |  | N/A
Customer service issues resulting from incomplete or inacurate data | Reputation (customers: missed deliveries, invoicing mistakes) Financial (performance penalties) | 1.1083 | 1.2125 | The ERP may continue to generate data output that appears correct until reviewed by another party. | Human error or Software error, (syntactical or bug) | N/A
ERP implementation unavailiable or unusable | Financial ( productivity), | 1.086 | 1.184 | The system performance results in workers taking longer to perform their tasks than with the existing spreadsheet systems | Technical system capacity or performance planning, | Installation & UAT
ACME staff slow or resistent to adopting ERP workflow | Business operations, financial, reputational | 1.0642 | 1.2735 | Users and business functions continue to rely on legacy spreadsheet mode of operation | Organizational culture, implementation approach, lack of leadership support, lack of useer training | Installation and UAT
ERP implementation delays lead to cost overruns | Financial | 1.0552 | 1.2913 | Existing business process(es) require ERP software configuration outside of standard implementation | Acme unaware of process complexity or all business areas involved in process Implementation team is not capable of identifying resolutions | Installation & UAT
ERP developers can not produce feature enhancements Acme requires | Business operations, financial, reputational | 1.05 | 1.05 | Changes to business operational requirements over time must be anticpated | Supply chain management error Management decision to use in house resources | Operations & Maintenance
CIRT does not maintain high level of readiness through regular CIRT exercises in response/recovery. | Full Spectrum of risk based on exponential impact to multiple systems | 0.96667 | 0.96667 | Response/recovery in real world incident is delayed and inefective |  | N/A
ACME IT department unable to adequately support ERP environment | Full Spectrum of risk based on exponential impact to multiple systems | 0.94833 | 1.21 | Unplanned service disruptions to certain ERP capabilites or the entire system extend for hours, days or occur frequently in business hours | ERP support may require specialized skills that are not adequately funded | Operations & Maintenance
Initial customization creates future maintenance difficulties and technical debt | Operational, Financial, Reputational (including this team who recommended the selection) | 0.93358 | 1.0937 | Limitations with the ERP selected can only be resolved through bespoke modifications | Senior management unprepared to support setbacks uncovered during implementation. | System Design Development
ERP implementation requirments create resource conflicts with existing operational staff | Financial, reputational (internal stakeholders) | 0.9 | 0.9 | Current business operations need to run in parallel while new ERP is implemented, tested and transferred into production | Senior management unprepared to fund additional resources, Project management failing to identify constraints early and escalate resolutions | N/A
Modifications to one ERP module unknowingly affect other modules resulting in incomplete or inacurate data | Full Spectrum of risk based on exponential impact to multiple systems | 0.88833 | 0.97375 | Delay in discovery of erroneous data use or malware spread results in multiple system involvement, delayed response/recovery and potential fines or civil litigation | The complexity of change not adequately addressed | Testing
Organizational change delays lead to cost overruns | Financial, reputational (internal stakeholders) | 0.76667 | 0.76667 | Business process changes to meet ERM requirements difficult to implement in various Acme business areas | Limited understanding of current operational requirements Employees not aligned with senior management | Installation & UAT
Limited benefits realization results in board of directors/investor confidence issue | Business operations, financial, reputational | 0.741 | 0.9685 | Implementation issues lead to only basic ERP capabilities in place or inability to retire some legacy processes | Senior management unprepared to support setbacks uncovered during implementation. | System Analysis & Requirements
ERP Developers fail to timely, discover, inform and patch for new vulnerabilities. | Full Spectrum of risk based on exponential impact to multiple systems | 0.696 | 0.788 | Security Patches are not implemented quickly enough to prevent a breach or exploited vulnerability |  | Operations & Maintenance
ERP software obselecance due to vendor failure or development team failure | Operational, Financial, Reputational | 0.66875 | 0.985 | All software will become obsolete, which lifecycle management approach best fits ACME. |  | Operations & Maintenance
Difficulty/inability to import or export data leads to solution lock-in or parallel sysems | Loss of revenue, loss of efficiency/employee satisfaction | 0.57867 | 0.74434 | Existing organizational data must put into the ERP, data will need to be extract in the future when moving to a new platform | Lack of enterprise architecture and data requirements | Development (technical debt) System Design
ERP developers can not produce vulnerabilty fixes at the rate Acme requires | Full Spectrum of risk based on exponential impact to multiple systems | 0.556 | 0.748 | Software updates will be needed to mitigate security vulnerabilties when they are discovered - Custom solutions result in delays (extended vulnerability timeframe) | Supply chain management error Management decision to use in house resources | Operations & Maintenance
ERP solution lacks reporting capability for transactions that potentially violate segregation of duties controls | Financial, reputational (internal stakeholders) | 0.30767 | 0.4225 | The ability to monitor transactions for potential issues and highlight those that must be manually reviewed is an important detective control |  | System Analysis & Requirements
Lack of legal recourse to recover costs due to ERP implementation or performance failure | Financial | 0.3 | 0.3 | Damage claims by ERP clients are not uncommon, | Supply chain management error Management decision to use in house resources | N/A
ERP solution lacks adequately robust role based access controls to enforce the segregation of duties required | Business operations, financial | 0.20025 | 0.3 | Segregation of duties is a key control for preventing fraud, misuse or misallocation of enterprise resources |  | System Analysis & Requirements

## SDLC Risks
SDLC Risk Category | Max score | Median Score | Risks Identified
System Design | 1.65 | 0.93358 | 3
Testing | 1.65 | 1.2692 | 2
Non-SDLC ERM risks | 1.2375 | 1.0375 | 6
Installation & UAT | 1.0642 | 1.0552 | 4
Operations & Maintenance | 1.05 | 0.696 | 5
Development | 0.93358 | 0.75613 | 2
System Analysis & Requirements | 0.741 | 0.30767 | 3
25

## Known ERP Implementation Risks
Impact SME1 | Probability SME1 | Impact SME2 | Probability SME2 | Impact SME3 | Probability SME3 | Impact SME4 | Probability SME4 | Impact SME5 | Probability SME5 | Risk ID | Risk | Risk Receptor | Primary or Seconday Loss | Potential Impact Description | Root Cause | Triggers | SDLC Phase
4 | 0.2 | 3 | 0.35 | 3 | 0.3 | 3 | 0.3 |  |  | 1 | Initial customization creates future maintenance difficulties and technical debt | Operational, Financial, Reputational (including this team who recommended the selection) | Secondary | Limitations with the ERP selected can only be resolved through bespoke modifications | Senior management unprepared to support setbacks uncovered during implementation. | Time and cost presures on project deliverlables can result in workaround solutions. | System Design Development
2 | 0.2 | 3 | 0.3 | 4 | 0.2 | 2 | 0.3 |  |  | 2 | ERP software obselecance due to vendor failure or development team failure | Operational, Financial, Reputational | Secondary | All software will become obsolete, which lifecycle management approach best fits ACME. |  |  | Operations & Maintenance
2 | 0.3 | 2 | 0.2 | 3 | 0.2 | 4 | 0.2 |  |  | 3 | Difficulty/inability to import or export data leads to solution lock-in or parallel sysems | Loss of revenue, loss of efficiency/employee satisfaction | Primary | Existing organizational data must put into the ERP, data will need to be extract in the future when moving to a new platform | Lack of enterprise architecture and data requirements | Proprietary data storage, lack of prebuilt extract, transform and load capabilities , Limited use of common open standards such as rest APIs | Development (technical debt) System Design
3 | 0.1 | 3 | 0.1 | 3 | 0.1 | 3 | 0.1 |  |  | 4 | Lack of legal recourse to recover costs due to ERP implementation or performance failure | Financial | Secondary | Damage claims by ERP clients are not uncommon, | Supply chain management error Management decision to use in house resources | Contracts limit liablity of the software vendor and/or implementer The company develops it's own software and assumes all related risks | N/A
[18 empty] | Proposed Controls from NIST SP800-53 | Category/Type of Controls
2 | 0.5 | 3 | 0.4 | 3 | 0.4 | 3 | 0.4 |  |  | 5 | ERP implementation delays lead to cost overruns | Financial | Primary | Existing business process(es) require ERP software configuration outside of standard implementation | Acme unaware of process complexity or all business areas involved in process Implementation team is not capable of identifying resolutions | Unforseen difficulty modeling existing business process(es) in ERP software | Installation and UAT | SLA | Admin
2 | 0.5 | 2 | 0.5 | 2 | 0.25 | 2 | 0.3 |  |  | 6 | Organizational change delays lead to cost overruns | Financial, reputational (internal stakeholders) | Primary | Business process changes to meet ERM requirements difficult to implement in various Acme business areas | Limited understanding of current operational requirements Employees not aligned with senior management | ERP implementation delays due to business process change requirements | Installation and UAT | Internal SLA | Admin
2 | 0.6 | 2 | 0.6 | 2 | 0.3 | 2 | 0.3 |  |  | 7 | ERP implementation requirments create resource conflicts with existing operational staff | Financial, reputational (internal stakeholders) | Primary | Current business operations need to run in parallel while new ERP is implemented, tested and transferred into production | Senior management unprepared to fund additional resources, Project management failing to identify constraints early and escalate resolutions |  | N/A | Internal SLA | Admin
4 | 0.7 | 4 | 0.15 | 4 | 0.3 | 5 | 0.2 |  |  | 8 | A databreach within the ERP system could result in customer record loss or compromise | Financial (fines, settlements) Reputation (customer confidence) | Primary & Secondary | Unauthorized access or release of PII or intelectual property | lack of application security and data encryption at rest | System compromise such as data theft through application injection, ransomware or poor IT management practices | N/A | Access Control Suite as applicable | Admin/Technical
3 | 0.2 | 2 | 0.2 | 3 | 0.2 | 4 | 0.2 |  |  | 9 | ERP developers can not produce vulnerabilty fixes at the rate Acme requires | Full Spectrum of risk based on exponential impact to multiple systems | Primary | Software updates will be needed to mitigate security vulnerabilties when they are discovered - Custom solutions result in delays (extended vulnerability timeframe) | Supply chain management error Management decision to use in house resources | Vendor or project community is slow to release security fixes or they are not stable Internal development team lacks expertise or time to develop security fixes | Operations & Maintenance | SLA, Automated Processes (RA-5 Automated Monitoring) (Implemented by Acme) | Admin/Technical
3 | 0.2 | 2 | 0.1 | 3 | 0.3 | 4 | 0.2 |  |  | 10 | ERP Developers fail to timely, discover, inform and patch for new vulnerabilities. | Full Spectrum of risk based on exponential impact to multiple systems | Primary | Security Patches are not implemented quickly enough to prevent a breach or exploited vulnerability |  |  | Operations & Maintenance | SLA, Automated Processes (RA-5 Automated Monitoring & Distribute) | Admin/Technical
2 | 0.4 | 2 | 0.4 | 2 | 0.5 | 2 | 0.6 |  |  | 11 | CIRT does not maintain high level of readiness through regular CIRT exercises in response/recovery. | Full Spectrum of risk based on exponential impact to multiple systems | Primary & Secondary | Response/recovery in real world incident is delayed and inefective |  |  | N/A | SLA (includes CIRT members from Developer), Policy (requires reglular CIRT exercises and AARs) | Admin
3 | 0.3 | 4 | 0.3 | 2 | 0.75 | 3 | 0.3 |  |  | 12 | ERP Developer does not offer Cyber Incident Response Team (CIRT) support | Full Spectrum of risk based on exponential impact to multiple systems | Primary | In-house staff must be trained in specialty skills or external cyber consultant retained to be part of CIRT. |  |  | N/A | SLA with external CIRT consultant, Internal training and exercises | Admin
3 | 0.6 | 2 | 0.4 | 3 | 0.2 | 3 | 0.4 |  |  | 13 | ERP implementation unavailiable or unusable | Financial ( productivity), | Primary | The system performance results in workers taking longer to perform their tasks than with the existing spreadsheet systems | Technical system capacity or performance planning, | System performance is unacceptable due to sizing or equipment failure | Installation and UAT | Business users participation in design decisions | Admin
3 | 0.7 | 2 | 0.7 | 2 | 0.3 | 2 | 0.4 |  |  | 14 | Business decision errors resulting from incomplete or inacurate data | Financial (forcasting, reporting) | Primary | The ERP may continue to generate data output that appears correct until reviewed by another party. | Human error or Software error, (syntactical or bug) | Users struggle with data input into the new system | N/A | Business users participation in UAT | Admin
3 | 0.7 | 2 | 0.2 | 2 | 0.3 | 3 | 0.4 |  |  | 15 | Customer service issues resulting from incomplete or inacurate data | Reputation (customers: missed deliveries, invoicing mistakes) Financial (performance penalties) | Secondary | The ERP may continue to generate data output that appears correct until reviewed by another party. | Human error or Software error, (syntactical or bug) | Users struggle with data input into the new system | N/A | Business users participation in UAT | Admin
2 | 0.4 | 2 | 0.3 | 3 | 0.35 | 2 | 0.3 |  |  | 16 | Modifications to one ERP module unknowingly affect other modules resulting in incomplete or inacurate data | Full Spectrum of risk based on exponential impact to multiple systems | Primary | Delay in discovery of erroneous data use or malware spread results in multiple system involvement, delayed response/recovery and potential fines or civil litigation | The complexity of change not adequately addressed | Time constraints on change implementation and testing, lack of funding for a comprehensive test and development area | Testing | IT department participation in design decisions, SLA requiring sysstem monitoring | Admin/Technical
3 | 0.5 | 2 | 0.4 | 4 | 0.2 | 3 | 0.2 |  |  | 17 | ACME IT department unable to adequately support ERP environment | Full Spectrum of risk based on exponential impact to multiple systems | Primary | Unplanned service disruptions to certain ERP capabilites or the entire system extend for hours, days or occur frequently in business hours | ERP support may require specialized skills that are not adequately funded | A complex architecture that is difficult to maintain SME orgnaizations often have limited I.T. specialist resources | Operations & Maintenance | Internal SLA | Admin
2 | 0.5 | 2 | 0.35 | 2 | 0.2 | 3 | 0.2 |  |  | 18 | Limited benefits realization results in board of directors/investor confidence issue | Business operations, financial, reputational | Secondary | Implementation issues lead to only basic ERP capabilities in place or inability to retire some legacy processes | Senior management unprepared to support setbacks uncovered during implementation. | Communication issues between departments, project management fails to identify and escalate risks and roadblocks | System Analysis & Requirements |  | Admin
3 | 0.6 | 2 | 0.35 | 2 | 0.4 | 2 | 0.4 |  |  | 19 | ACME staff slow or resistent to adopting ERP workflow | Business operations, financial, reputational | Primary | Users and business functions continue to rely on legacy spreadsheet mode of operation | Organizational culture, implementation approach, lack of leadership support, lack of useer training | Workers citiing system inacuracy, system use difficulty or tacit management acceptance of poor adoption | Installation and UAT | Management inforced decison | Admin
3 | 0.5 | 3 | 0.4 | 3 | 0.2 | 3 | 0.3 |  |  | 20 | ERP developers can not produce feature enhancements Acme requires | Business operations, financial, reputational | Primary | Changes to business operational requirements over time must be anticpated | Supply chain management error Management decision to use in house resources | Vendor or project community is slow to release new features or they are not stable Internal development team lacks expertise or time to develop new features | Operations & Maintenance | SLA, Internal SLA | Admin
2 | 0.2 | 2 | 0.2 | 2 | 0.1 | 2 | 0.1 |  |  | 21 | ERP solution lacks adequately robust role based access controls to enforce the segregation of duties required | Business operations, financial | Primary & Secondary | Segregation of duties is a key control for preventing fraud, misuse or misallocation of enterprise resources |  |  | System Analysis & Requirements | SLA requiring audits and automated monitoring | Admin/Technical
2 | 0.2 | 1 | 0.4 | 2 | 0.1 | 2 | 0.1 |  |  | 22 | ERP solution lacks reporting capability for transactions that potentially violate segregation of duties controls | Financial, reputational (internal stakeholders) | Secondary | The ability to monitor transactions for potential issues and highlight those that must be manually reviewed is an important detective control |  |  | System Analysis & Requirements | SLA requiring audits | Admin
ISO 27001 "top ten"
Impact Rank | Probability | [9 empty] | Threat Agent (source of threat or person who initiates threat) | Threats | Primary or Secondary Loss | TA Motivation |  | Social Engineering
3 | 0.1 | 2 | 0.1 | 3 | 0.1 | 2 | 0.1 |  |  | ISO1 | Vandals/terrorists/Corporate raiders/professional criminals/hackers/ rogue; State | Denial of service attack / flood / buffer overflow | Primary | Disrupt business operations by making systems and data unavailable |  | Access to the network by unathorized persons |  | Continuous Monitoring, Network Segregation | Technical
5 | 0.8 | 4 | 0.15 | 5 | 0.4 | 4 | 0.4 |  |  | ISO2 | Corporate raiders/professional criminals/hackers | Spoofing of credentials / bypass authentication | Primary | Gain unauthorized access for multiple pruposes |  | Disclosure of information or passwords |  | MFA, Continuous Monitoring, IDS/IPS, SIEM, Prevention of Tailgating and Over the Shoulder threats | Technical/Physical
|  |  |  | 4 | 0.35 | 4 | 0.4 |  |  | ISO3 | Marketing companies, online service providers, malicious attackers | Large-scale and/or inappropriate data mining and/or surveillance |  | To collect large volume of potentially personal sensitive data for market analysis and profit making (H) |  | Malfunction of equipment |  | Continuous Monitoring, IDS/IPS, SIEM, Prevention of Tailgating and Over the Shoulder threats, dumpster diving | Technical/Physical
4 | 0.7 | 2 | 0.05 | 3 | 0.3 | 3 | 0.2 |  |  | ISO4 | Corporate raiders/professional criminals/hackers | Traffic analysis / scan / probe | Primary & Secondary | Gain unauthorized access to data to steal intellectual property, or financial gain via ransomware, or to steal credential for additional access and/or escalation of privelege |  | Loss of electricity |  | MFA, Continuous Monitoring, IDS/IPS, SIEM, Security awareness trainings | Technical
5 |  | 1 | 0.05 | 4 | 0.2 | 4 | 0.2 |  |  | ISO5 | Hacker | Man-in-the-middle attack | Secondary | To hijack network communication channel for sensitive data collection and misinformation feeding and identity theft (HML) |  | Errors in maintenance |  | TLS encryption protocol | Technical
5 | 0.8 | 1 | 0.4 | 3 | 0.5 | 2 | 0.6 |  |  | ISO6 | Hacker, criminal, terrorists | Social engineering attack | Primary & Secondary | To obtain sensitive information and/or system access credentials |  | Theft of hardware |  | Continuous Monitoring, IDS/IPS, SIEM, Security awareness trainigns | Technical
3 | 0.2 | 1 | 0.1 | 3 | 0.3 | 2 | 0.2 |  |  | ISO7 | Malicious attacker | Theft [of cards, devices etc] | Primary | Financial gain, criminal activities, or disruption of services |  | Destruction of records |  | MFA and Physical security controls | Technical
4 | 0.7 | 2 | 0.1 | 4 | 0.2 | 4 | 0.2 |  |  | ISO8 | Malicious attacker | Unauthorised access to / deletion / modification of devices / data etc. | Primary | Financial gain, criminal activities, or disruption of services |  | Human or natural disasters |  | Continuous Monitoring, Strenghten security in external facing devices | Technical
3 | 0.4 | 2 | 0.1 | 3 | 0.2 | 3 | 0.2 |  |  | ISO9 | Insider threat - Unintentional or deliberate | Loss or misuse [of cards, devices etc] | Primary & Secondary | Human error, deliberate sabatage |  | Terrorist attacks |  | MFA | Technical
|  | 2 | 0.2 | 3 | 0.2 | 3 | 0.4 |  |  | ISO10 | Insider threat - Unintentional or deliberate | Use erroneous and/or unreliable data | Secondary | Human error, deliberate sabatage |  |  |  | Continuous Monitoring, IDS/IPS, SIEM | Technical
Note on L31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is this an appliclabe threat for an internal ERP?

## FAIR Analysis
Impact SME1 | Probability SME1 | Impact SME2 | Probability SME2 | Impact SME3 | Probability SME3 | Impact SME4 | Probability SME4 | Impact SME5 | Probability SME5 | Risk ID | Impact Range (min X 100) | Impact Range (max X 100) | Probability Range (min) | Probability Range (max) | Impact Range ( Random) | MC Calc | MC Median | MC Max | MC1 | MC2 | MC3 | MC4 | MC5 | MC6 | MC7 | MC8 | MC9 | MC10 | Min | 4ML | Max | PERT LEF
4 | 0.2 | 3 | 0.35 | 3 | 0.3 | 3 | 0.3 |  |  | 1 | 300 | 400 | 0.2 | 0.35 | 3.5 | 0.99167 | 0.93358 | 1.0937 | 0.88967 | 0.935 | 0.88117 | 1.0002 | 1.037 | 0.93217 | 1.0937 | 0.88683 | 0.87267 | 0.96333 | 0.2 | 1.15 | 0.35 | 0.28333
2 | 0.2 | 3 | 0.3 | 4 | 0.2 | 2 | 0.3 |  |  | 2 | 200 | 400 | 0.2 | 0.3 | 3.52 | 0.88 | 0.66875 | 0.985 | 0.5175 | 0.5225 | 0.5375 | 0.9625 | 0.6 | 0.7375 | 0.985 | 0.525 | 0.79 | 0.8775 | 0.2 | 1 | 0.3 | 0.25
2 | 0.3 | 2 | 0.2 | 3 | 0.2 | 4 | 0.2 |  |  | 3 | 200 | 400 | 0.2 | 0.3 | 3.9 | 0.91 | 0.57867 | 0.74433 | 0.59733 | 0.50167 | 0.665 | 0.74433 | 0.48533 | 0.50867 | 0.56 | 0.59733 | 0.55533 | 0.64167 | 0.2 | 0.9 | 0.3 | 0.23333
3 | 0.1 | 3 | 0.1 | 3 | 0.1 | 3 | 0.1 |  |  | 4 | 300 | 300 | 0.1 | 0.1 | 3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.1 | 0.4 | 0.1 | 0.1
2 | 0.5 | 3 | 0.4 | 3 | 0.4 | 3 | 0.4 |  |  | 5 | 200 | 300 | 0.4 | 0.5 | 2.25 | 0.975 | 1.0552 | 1.2913 | 0.87533 | 1.0313 | 1.027 | 1.079 | 1.17 | 0.95333 | 1.209 | 1.2003 | 0.86667 | 1.2913 | 0.4 | 1.7 | 0.5 | 0.43333
2 | 0.5 | 2 | 0.5 | 2 | 0.25 | 2 | 0.3 |  |  | 6 | 200 | 200 | 0.3 | 0.5 | 2 | 0.76667 | 0.76667 | 0.76667 | 0.76667 | 0.76667 | 0.76667 | 0.76667 | 0.76667 | 0.76667 | 0.76667 | 0.76667 | 0.76667 | 0.76667 | 0.25 | 1.55 | 0.5 | 0.38333
2 | 0.6 | 2 | 0.6 | 2 | 0.3 | 2 | 0.3 |  |  | 7 | 200 | 200 | 0.3 | 0.6 | 2 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.3 | 1.8 | 0.6 | 0.45
4 | 0.7 | 4 | 0.15 | 4 | 0.3 | 5 | 0.2 |  |  | 8 | 400 | 500 | 0.15 | 0.7 | 4.4 | 1.6133 | 1.65 | 1.826 | 1.65 | 1.6867 | 1.5803 | 1.826 | 1.65 | 1.7893 | 1.76 | 1.639 | 1.6023 | 1.5583 | 0.15 | 1.35 | 0.7 | 0.36667
3 | 0.2 | 2 | 0.2 | 3 | 0.2 | 4 | 0.2 |  |  | 9 | 200 | 400 | 0.2 | 0.2 | 2.65 | 0.53 | 0.556 | 0.748 | 0.474 | 0.442 | 0.726 | 0.472 | 0.456 | 0.638 | 0.66 | 0.448 | 0.732 | 0.748 | 0.2 | 0.8 | 0.2 | 0.2
3 | 0.2 | 2 | 0.1 | 3 | 0.3 | 4 | 0.2 |  |  | 10 | 200 | 400 | 0.1 | 0.3 | 2.29 | 0.458 | 0.696 | 0.788 | 0.416 | 0.708 | 0.684 | 0.58 | 0.42 | 0.788 | 0.722 | 0.716 | 0.77 | 0.514 | 0.1 | 0.8 | 0.3 | 0.2
2 | 0.4 | 2 | 0.4 | 2 | 0.5 | 2 | 0.6 |  |  | 11 | 200 | 200 | 0.4 | 0.6 | 2 | 0.96667 | 0.96667 | 0.96667 | 0.96667 | 0.96667 | 0.96667 | 0.96667 | 0.96667 | 0.96667 | 0.96667 | 0.96667 | 0.96667 | 0.96667 | 0.4 | 1.9 | 0.6 | 0.48333
3 | 0.3 | 4 | 0.3 | 2 | 0.75 | 3 | 0.3 |  |  | 12 | 200 | 400 | 0.3 | 0.75 | 2.18 | 0.981 | 1.2375 | 1.665 | 1.665 | 1.287 | 1.053 | 1.188 | 0.927 | 0.954 | 1.4445 | 1.4175 | 1.1025 | 1.485 | 0.3 | 1.65 | 0.75 | 0.45
3 | 0.6 | 2 | 0.4 | 3 | 0.2 | 3 | 0.4 |  |  | 13 | 200 | 300 | 0.2 | 0.6 | 2.27 | 0.908 | 1.086 | 1.184 | 1.184 | 1.044 | 1.076 | 1.176 | 0.824 | 0.908 | 1.128 | 1.096 | 0.952 | 1.136 | 0.2 | 1.6 | 0.6 | 0.4
3 | 0.7 | 2 | 0.7 | 2 | 0.3 | 2 | 0.4 |  |  | 14 | 200 | 300 | 0.3 | 0.7 | 2.22 | 1.147 | 1.364 | 1.5397 | 1.4828 | 1.4828 | 1.5397 | 1.3123 | 1.395 | 1.1625 | 1.2452 | 1.1987 | 1.5138 | 1.333 | 0.3 | 2.1 | 0.7 | 0.51667
3 | 0.7 | 2 | 0.2 | 2 | 0.3 | 3 | 0.4 |  |  | 15 | 200 | 300 | 0.2 | 0.7 | 2.39 | 0.99583 | 1.1083 | 1.2125 | 1.0708 | 1.2125 | 1.0917 | 1.1333 | 1.1458 | 1.125 | 1.175 | 0.85833 | 0.97917 | 0.9375 | 0.2 | 1.6 | 0.7 | 0.41667
2 | 0.4 | 2 | 0.3 | 3 | 0.35 | 2 | 0.3 |  |  | 16 | 200 | 300 | 0.3 | 0.4 | 2.32 | 0.79267 | 0.88833 | 0.97375 | 0.97033 | 0.78242 | 0.81317 | 0.90883 | 0.92592 | 0.73458 | 0.97375 | 0.89175 | 0.88492 | 0.85075 | 0.3 | 1.35 | 0.4 | 0.34167
3 | 0.5 | 2 | 0.4 | 4 | 0.2 | 3 | 0.2 |  |  | 17 | 200 | 400 | 0.2 | 0.5 | 3.21 | 1.07 | 0.94833 | 1.21 | 0.91 | 1.19 | 1.21 | 0.82667 | 1.17 | 0.98667 | 0.74667 | 0.68333 | 1.04 | 0.82333 | 0.2 | 1.3 | 0.5 | 0.33333
2 | 0.5 | 2 | 0.35 | 2 | 0.2 | 3 | 0.2 |  |  | 18 | 200 | 300 | 0.2 | 0.5 | 2.6 | 0.845 | 0.741 | 0.9685 | 0.70525 | 0.702 | 0.7345 | 0.80925 | 0.82875 | 0.7475 | 0.806 | 0.676 | 0.65975 | 0.9685 | 0.2 | 1.25 | 0.5 | 0.325
3 | 0.6 | 2 | 0.35 | 2 | 0.4 | 2 | 0.4 |  |  | 19 | 200 | 300 | 0.35 | 0.6 | 2.64 | 1.188 | 1.0642 | 1.2735 | 1.062 | 1.188 | 1.116 | 1.026 | 0.9405 | 1.2735 | 1.0665 | 1.1655 | 1.0485 | 1.017 | 0.35 | 1.75 | 0.6 | 0.45
3 | 0.5 | 3 | 0.4 | 3 | 0.2 | 3 | 0.3 |  |  | 20 | 300 | 300 | 0.2 | 0.5 | 3 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 0.2 | 1.4 | 0.5 | 0.35
2 | 0.2 | 2 | 0.2 | 2 | 0.1 | 2 | 0.1 |  |  | 21 | 100 | 200 | 0.1 | 0.2 | 1.95 | 0.2925 | 0.20025 | 0.3 | 0.159 | 0.1545 | 0.165 | 0.168 | 0.186 | 0.2145 | 0.219 | 0.3 | 0.252 | 0.2325 | 0.1 | 0.6 | 0.2 | 0.15
2 | 0.2 | 1 | 0.4 | 2 | 0.1 | 2 | 0.1 |  |  | 22 | 100 | 200 | 0.1 | 0.4 | 1.39 | 0.30117 | 0.30767 | 0.4225 | 0.29033 | 0.38133 | 0.3055 | 0.30767 | 0.30767 | 0.234 | 0.32283 | 0.24917 | 0.42033 | 0.4225 | 0.1 | 0.8 | 0.4 | 0.21667

## Status_Report_Preliminary_Risks
Risk ID | Risk | Risk Receptor | Primary or Seconday Loss | Potential Impact Description
1 | Initial customization creates future maintenance difficulties and technical debt | Operational, Financial, Reputational (including this team who recommended the selection) | Secondary | Limitations with the ERP selected can only be resolved through bespoke modifications
2 | ERP software obselecance due to vendor failure or development team failure | Operational, Financial, Reputational | Secondary | All software will become obsolete, which lifecycle management approach best fits ACME.
3 | Difficulty/inability to import or export data leads to solution lock-in or parallel sysems | Loss of revenue, loss of efficiency/employee satisfaction | Primary | Existing organizational data must put into the ERP, data will need to be extract in the future when moving to a new platform
4 | Lack of legal recourse to recover costs due to ERP implementation or performance failure | Financial | Secondary | Damage claims by ERP clients are not uncommon,
5 | ERP implementation delays lead to cost overruns | Financial | Primary | Existing business process(es) require ERP software configuration outside of standard implementation
6 | Organizational change delays lead to cost overruns | Financial, reputational (internal stakeholders) | Primary | Business process changes to meet ERM requirements difficult to implement in various Acme business areas
7 | ERP implementation requirments create resource conflicts with existing operational staff | Financial, reputational (internal stakeholders) | Primary | Current business operations need to run in parallel while new ERP is implemented, tested and transferred into production
8 | A databreach within the ERP system could result in customer record loss or compromise | Financial (fines, settlements) Reputation (customer confidence) | Primary & Secondary | Unauthorized access or release of PII or intelectual property
9 | ERP developers can not produce vulnerabilty fixes at the rate Acme requires | Full Spectrum of risk based on exponential impact to multiple systems | Primary | Software updates will be needed to mitigate security vulnerabilties when they are discovered - Custom solutions result in delays (extended vulnerability timeframe)
10 | ERP Developers fail to timely, discover, inform and patch for new vulnerabilities. | Full Spectrum of risk based on exponential impact to multiple systems | Primary | Security Patches are not implemented quickly enough to prevent a breach or exploited vulnerability
11 | CIRT does not maintain high level of readiness through regular CIRT exercises in response/recovery. | Full Spectrum of risk based on exponential impact to multiple systems | Primary & Secondary | Response/recovery in real world incident is delayed and inefective
12 | ERP Developer does not offer Cyber Incident Response Team (CIRT) support | Full Spectrum of risk based on exponential impact to multiple systems | Primary | In-house staff must be trained in specialty skills or external cyber consultant retained to be part of CIRT.
13 | ERP implementation unavailiable or unusable | Financial ( productivity), | Primary | The system performance results in workers taking longer to perform their tasks than with the existing spreadsheet systems
14 | Business decision errors resulting from incomplete or inacurate data | Financial (forcasting, reporting) | Primary | The ERP may continue to generate data output that appears correct until reviewed by another party.
15 | Customer service issues resulting from incomplete or inacurate data | Reputation (customers: missed deliveries, invoicing mistakes) Financial (performance penalties) | Secondary | The ERP may continue to generate data output that appears correct until reviewed by another party.
16 | Modifications to one ERP module unknowingly affect other modules resulting in incomplete or inacurate data | Full Spectrum of risk based on exponential impact to multiple systems | Primary | Delay in discovery of erroneous data use or malware spread results in multiple system involvement, delayed response/recovery and potential fines or civil litigation
17 | ACME IT department unable to adequately support ERP environment | Full Spectrum of risk based on exponential impact to multiple systems | Primary | Unplanned service disruptions to certain ERP capabilites or the entire system extend for hours, days or occur frequently in business hours
18 | Limited benefits realization results in board of directors/investor confidence issue | Business operations, financial, reputational | Secondary | Implementation issues lead to only basic ERP capabilities in place or inability to retire some legacy processes
19 | ACME staff slow or resistent to adopting ERP workflow | Business operations, financial, reputational | Primary | Users and business functions continue to rely on legacy spreadsheet mode of operation
20 | ERP developers can not produce feature enhancements Acme requires | Business operations, financial, reputational | Primary | Changes to business operational requirements over time must be anticpated
21 | ERP solution lacks adequately robust role based access controls to enforce the segregation of duties required | Business operations, financial | Primary & Secondary | Segregation of duties is a key control for preventing fraud, misuse or misallocation of enterprise resources
22 | ERP solution lacks reporting capability for transactions that potentially violate segregation of duties controls | Financial, reputational (internal stakeholders) | Secondary | The ability to monitor transactions for potential issues and highlight those that must be manually reviewed is an important detective control
ISO 27001 "top ten"
| Threat Agent (source of threat or person who initiates threat) | Threats | Primary or Secondary Loss | TA Motivation
ISO1 | Vandals/terrorists/Corporate raiders/professional criminals/hackers/ rogue; State | Denial of service attack / flood / buffer overflow | Primary | Disrupt business operations by making systems and data unavailable
ISO2 | Corporate raiders/professional criminals/hackers | Spoofing of credentials / bypass authentication | Primary | Gain unauthorized access for multiple pruposes
ISO3 N/A | Marketing companies, online service providers, malicious attackers | Large-scale and/or inappropriate data mining and/or surveillance |  | To collect large volume of potentially personal sensitive data for market analysis and profit making (H)
ISO4 | Corporate raiders/professional criminals/hackers | Traffic analysis / scan / probe | Primary & Secondary | Gain unauthorized access to data to steal intellectual property, or financial gain via ransomware, or to steal credential for additional access and/or escalation of privelege
ISO5 | Hacker | Man-in-the-middle attack | Secondary | To hijack network communication channel for sensitive data collection and misinformation feeding and identity theft (HML)
ISO6 | Hacker, criminal, terrorists | Social engineering attack | Primary & Secondary | To obtain sensitive information and/or system access credentials
ISO7 | Malicious attacker | Theft [of cards, devices etc] | Primary | Financial gain, criminal activities, or disruption of services
ISO8 | Malicious attacker | Unauthorised access to / deletion / modification of devices / data etc. | Primary | Financial gain, criminal activities, or disruption of services
ISO9 | Insider threat - Unintentional or deliberate | Loss or misuse [of cards, devices etc] | Primary & Secondary | Human error, deliberate sabatage
ISO10 | Insider threat - Unintentional or deliberate | Use erroneous and/or unreliable data | Secondary | Human error, deliberate sabatage

## 27001-Generic-Threats
Threat ID | Threats | Threat Agent (source of threat or person who initiates threat) | TA Motivation
T1 | Denial of service attack / flood / buffer overflow | Vandals/terrorists/Corporate raiders/professional criminals/hackers/ rogue; State | Medium
T2 | Spoofing of credentials / bypass authentication | Corporate raiders/professional criminals/hackers | Medium
T3 | Large-scale and/or inappropriate data mining and/or surveillance | Marketing companies, online service providers, malicious attackers | To collect large volume of potentially personal sensitive data for market analysis and profit making (H)
T4 | Traffic analysis / scan / probe | Corporate raiders/professional criminals/hackers
T5 | Man-in-the-middle attack | Hacker | To hijack network communication channel for sensitive data collection and misinformation feeding and identity theft (HML)
T6 | Social engineering attack | Hacker, criminal, terrorists | To obtain sensitive information and system penetration
T7 | Theft [of cards, devices etc] | Malicious attacker | Financial gain, criminal activities (H)
T8 | Unauthorised access to / deletion / modification of devices / data etc. | Malicious attacker
T9 | Loss or misuse [of cards, devices etc] | Passenger, airport and airline personnel
T10 | Use erroneous and/or unreliable data
T11 | Procedures / instructions not followed | Airport and airline personnel. Passengers
T12 | Non-compliance with data protection legislation | Commercial establishments, State
T13 | Function creep (data used for other purposes than the ones for which they were originally collected) | Commercial establishments
T14 | Unauthorized check-in and boarding / identity theft | Hacker, criminal, terrorist
T15 | Cloning of credentials and tags (rfid related) | Hacker | Medium-High
T16 | Unauthorised access to other restricted areas (apart from boarding e.g. Control room, personnel's' offices) | Hacker, criminal, terrorist
T17 | Side channel attack
T18 | Blocking
T19 | Jamming | Hacker | System operation interruption to futher achieve attack steps such as spoofing or decoyed attacks (L)
T20 | Fake / rogue rfid readers / scanning of rfid reader and /or tag
T21 | Physical rfid tag destruction
T22 | Malfunctioning/breakdown of systems /devices / equipment | n/a | n/a
T23 | E-visa not accepted at check in | system fault
T24 | Worms, viruses & malicious code | Hacker, rogue state | Service disruption, system compromise, information theft
T25 | Malicious attack on power systems | Malicious attacker
T26 | State surveillance on citizens | State | To achieve unethical citizen control political agenda (H)
T27 | Trade union/labour strikes | Labor union
T28 | Adverse weather condition or other disaster | n/a | n/a
T29 | Ad hoc network routing attack | Corporate raiders/professional criminals/hackers | Initial attack step to further achieve cloning, man-in-the-middle attack, or service interruption which leads to system compromise (M)
T30 | Low acceptance of devices / equipment / procedures | Passengers / citizens / airport & airline personnel
T31 | Data linkability | Commercial establishments, State
T32 | Profiling | Commercial establishments, State
T33 | Exclusion of the data subject from the data processing process | Commercial establishments, State
T34 | Trivialisation of unique identifiers | Commercial establishments, State

## ERM Risk List
Risk ID | Risk | Risk Receptor | Primary or Seconday Loss | Potential Impact Description | Root Cause | Triggers
1 | Initial customization creates future maintenance difficulties and technical debt | Operational, Financial, Reputational (including this team who recommended the selection) | Secondary | Limitations with the ERP selected can only be resolved through bespoke modifications | Senior management unprepared to support setbacks uncovered during implementation. | Time and cost presures on project deliverlables can result in workaround solutions.
2 | ERP software obselecance due to vendor failure or development team failure | Operational, Financial, Reputational | Secondary | All software will become obsolete, which lifecycle management approach best fits ACME.
3 | Difficulty/inability to import or export data leads to solution lock-in or parallel sysems | Loss of revenue, loss of efficiency/employee satisfaction | Primary | Existing organizational data must put into the ERP, data will need to be extract in the future when moving to a new platform | Lack of enterprise architecture and data requirements | Proprietary data storage, lack of prebuilt extract, transform and load capabilities , Limited use of common open standards such as rest APIs
4 | Lack of legal recourse to recover costs due to ERP implementation or performance failure | Financial | Secondary | Damage claims by ERP clients are not uncommon, | Supply chain management error Management decision to use in house resources | Contracts limit liablity of the software vendor and/or implementer The company develops it's own software and assumes all related risks
[7 empty] | Proposed Controls from NIST SP800-53 | Category/Type of Controls
5 | ERP implementation delays lead to cost overruns | Financial | Primary | Existing business process(es) require ERP software configuration outside of standard implementation | Acme unaware of process complexity or all business areas involved in process Implementation team is not capable of identifying resolutions | Unforseen difficulty modeling existing business process(es) in ERP software | SLA | Admin
6 | Organizational change delays lead to cost overruns | Financial, reputational (internal stakeholders) | Primary | Business process changes to meet ERM requirements difficult to implement in various Acme business areas | Limited understanding of current operational requirements Employees not aligned with senior management | ERP implementation delays due to business process change requirements | Internal SLA | Admin
7 | ERP implementation requirments create resource conflicts with existing operational staff | Financial, reputational (internal stakeholders) | Primary | Current business operations need to run in parallel while new ERP is implemented, tested and transferred into production | Senior management unprepared to fund additional resources, Project management failing to identify constraints early and escalate resolutions |  | Internal SLA | Admin
8 | A databreach within the ERP system could result in customer record loss or compromise | Financial (fines, settlements) Reputation (customer confidence) | Primary & Secondary | Unauthorized access or release of PII or intelectual property | lack of application security and data encryption at rest | System compromise such as data theft through application injection, ransomware or poor IT management practices | Access Control Suite as applicable | Admin/Technical
9 | ERP developers can not produce vulnerabilty fixes at the rate Acme requires | Full Spectrum of risk based on exponential impact to multiple systems | Primary | Software updates will be needed to mitigate security vulnerabilties when they are discovered - Custom solutions result in delays (extended vulnerability timeframe) | Supply chain management error Management decision to use in house resources | Vendor or project community is slow to release security fixes or they are not stable Internal development team lacks expertise or time to develop security fixes | SLA, Automated Processes (RA-5 Automated Monitoring) (Implemented by Acme) | Admin/Technical
10 | ERP Developers fail to timely, discover, inform and patch for new vulnerabilities. | Full Spectrum of risk based on exponential impact to multiple systems | Primary | Security Patches are not implemented quickly enough to prevent a breach or exploited vulnerability |  |  | SLA, Automated Processes (RA-5 Automated Monitoring & Distribute) | Admin/Technical
11 | CIRT does not maintain high level of readiness through regular CIRT exercises in response/recovery. | Full Spectrum of risk based on exponential impact to multiple systems | Primary & Secondary | Response/recovery in real world incident is delayed and inefective |  |  | SLA (includes CIRT members from Developer), Policy (requires reglular CIRT exercises and AARs) | Admin
12 | ERP Developer does not offer Cyber Incident Response Team (CIRT) support | Full Spectrum of risk based on exponential impact to multiple systems | Primary | In-house staff must be trained in specialty skills or external cyber consultant retained to be part of CIRT. |  |  | SLA with external CIRT consultant, Internal training and exercises | Admin
13 | ERP implementation unavailiable or unusable | Financial ( productivity), | Primary | The system performance results in workers taking longer to perform their tasks than with the existing spreadsheet systems | Technical system capacity or performance planning, | System performance is unacceptable due to sizing or equipment failure | Business users participation in design decisions | Admin
14 | Business decision errors resulting from incomplete or inacurate data | Financial (forcasting, reporting) | Primary | The ERP may continue to generate data output that appears correct until reviewed by another party. | Human error or Software error, (syntactical or bug) | Users struggle with data input into the new system | Business users participation in UAT | Admin
15 | Customer service issues resulting from incomplete or inacurate data | Reputation (customers: missed deliveries, invoicing mistakes) Financial (performance penalties) | Secondary | The ERP may continue to generate data output that appears correct until reviewed by another party. | Human error or Software error, (syntactical or bug) | Users struggle with data input into the new system | Business users participation in UAT | Admin
16 | Modifications to one ERP module unknowingly affect other modules resulting in incomplete or inacurate data | Full Spectrum of risk based on exponential impact to multiple systems | Primary | Delay in discovery of erroneous data use or malware spread results in multiple system involvement, delayed response/recovery and potential fines or civil litigation | The complexity of change not adequately addressed | Time constraints on change implementation and testing, lack of funding for a comprehensive test and development area | IT department participation in design decisions, SLA requiring sysstem monitoring | Admin/Technical
17 | ACME IT department unable to adequately support ERP environment | Full Spectrum of risk based on exponential impact to multiple systems | Primary | Unplanned service disruptions to certain ERP capabilites or the entire system extend for hours, days or occur frequently in business hours | ERP support may require specialized skills that are not adequately funded | A complex architecture that is difficult to maintain SME orgnaizations often have limited I.T. specialist resources | Internal SLA | Admin
18 | Limited benefits realization results in board of directors/investor confidence issue | Business operations, financial, reputational | Secondary | Implementation issues lead to only basic ERP capabilities in place or inability to retire some legacy processes | Senior management unprepared to support setbacks uncovered during implementation. | Communication issues between departments, project management fails to identify and escalate risks and roadblocks |  | Admin
19 | ACME staff slow or resistent to adopting ERP workflow | Business operations, financial, reputational | Primary | Users and business functions continue to rely on legacy spreadsheet mode of operation | Organizational culture, implementation approach, lack of leadership support, lack of useer training | Workers citiing system inacuracy, system use difficulty or tacit management acceptance of poor adoption | Management inforced decison | Admin
20 | ERP developers can not produce feature enhancements Acme requires | Business operations, financial, reputational | Primary | Changes to business operational requirements over time must be anticpated | Supply chain management error Management decision to use in house resources | Vendor or project community is slow to release new features or they are not stable Internal development team lacks expertise or time to develop new features | SLA, Internal SLA | Admin
21 | ERP solution lacks adequately robust role based access controls to enforce the segregation of duties required | Business operations, financial | Primary & Secondary | Segregation of duties is a key control for preventing fraud, misuse or misallocation of enterprise resources |  |  | SLA requiring audits and automated monitoring | Admin/Technical
22 | ERP solution lacks reporting capability for transactions that potentially violate segregation of duties controls | Financial, reputational (internal stakeholders) | Secondary | The ability to monitor transactions for potential issues and highlight those that must be manually reviewed is an important detective control |  |  | SLA requiring audits | Admin
ISO 27001 "top ten"
| Threat Agent (source of threat or person who initiates threat) | Threats | Primary or Secondary Loss | TA Motivation |  | Social Engineering
ISO1 | Vandals/terrorists/Corporate raiders/professional criminals/hackers/ rogue; State | Denial of service attack / flood / buffer overflow | Primary | Disrupt business operations by making systems and data unavailable |  | Access to the network by unathorized persons | Continuous Monitoring, Network Segregation | Technical
ISO2 | Corporate raiders/professional criminals/hackers | Spoofing of credentials / bypass authentication | Primary | Gain unauthorized access for multiple pruposes |  | Disclosure of information or passwords | MFA, Continuous Monitoring, IDS/IPS, SIEM, Prevention of Tailgating and Over the Shoulder threats | Technical/Physical
ISO3 | Marketing companies, online service providers, malicious attackers | Large-scale and/or inappropriate data mining and/or surveillance |  | To collect large volume of potentially personal sensitive data for market analysis and profit making (H) |  | Malfunction of equipment | Continuous Monitoring, IDS/IPS, SIEM, Prevention of Tailgating and Over the Shoulder threats, dumpster diving | Technical/Physical
ISO4 | Corporate raiders/professional criminals/hackers | Traffic analysis / scan / probe | Primary & Secondary | Gain unauthorized access to data to steal intellectual property, or financial gain via ransomware, or to steal credential for additional access and/or escalation of privelege |  | Loss of electricity | MFA, Continuous Monitoring, IDS/IPS, SIEM, Security awareness trainings | Technical
ISO5 | Hacker | Man-in-the-middle attack | Secondary | To hijack network communication channel for sensitive data collection and misinformation feeding and identity theft (HML) |  | Errors in maintenance | TLS encryption protocol | Technical
ISO6 | Hacker, criminal, terrorists | Social engineering attack | Primary & Secondary | To obtain sensitive information and/or system access credentials |  | Theft of hardware | Continuous Monitoring, IDS/IPS, SIEM, Security awareness trainigns | Technical
ISO7 | Malicious attacker | Theft [of cards, devices etc] | Primary | Financial gain, criminal activities, or disruption of services |  | Destruction of records | MFA and Physical security controls | Technical
ISO8 | Malicious attacker | Unauthorised access to / deletion / modification of devices / data etc. | Primary | Financial gain, criminal activities, or disruption of services |  | Human or natural disasters | Continuous Monitoring, Strenghten security in external facing devices | Technical
ISO9 | Insider threat - Unintentional or deliberate | Loss or misuse [of cards, devices etc] | Primary & Secondary | Human error, deliberate sabatage |  | Terrorist attacks | MFA | Technical
ISO10 | Insider threat - Unintentional or deliberate | Use erroneous and/or unreliable data | Secondary | Human error, deliberate sabatage |  |  | Continuous Monitoring, IDS/IPS, SIEM | Technical
Note on B31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is this an appliclabe threat for an internal ERP?